| Submitting Organization |  |  |  |
| --- | --- | --- | --- |
| Organization Name | County(ies) of Service | Liaison Name | Liaison Email |
| Org A: Ontario County Public Health | Ontario | Kate Ott | kate.ott@ontariocountyny.gov |
| Is this a joint plan? Yes/No | Yes |  |  |
| Note: a joint plan is defined as submitting one Community Health Assessment and Community Health Improvement Plan for both the LHD(s) and hospital(s) within the same county. |  |  |  |

| Participating Organization(s) |  |  |  |
| --- | --- | --- | --- |
| Organization Name | County(ies) of Service | Liaison Name | Liaison Email |
| Org B: UR Medicine Finger Lakes Community Health | Ontario | Kim Ilacqua | kimberly_ilacqua@urmc.rochester.edu |
| Org C: UR Medicine FF Thompson Health | Ontario | Amanda Reynolds | amanda_reynolds@urmc.rochester.edu |
| Org D: Rochester Regional Health Clifton Springs Hospital and Clinic | Ontario | Hannah Smith | hannah.smith@rochesterregional.org |

| Healthcare Access & Quality | Instructions: Please review the Community Health Improvement Planning Guidance for the required elements of the Community Health Improvement Plan (CHIP) and Community Service Plan (CSP): https://www.health.ny.gov/prevention/prevention agenda/2025-2030/docs/letter and guidence.pdf. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Domain | Priority | Objective | Intervention | Disparities Being Addressed | Family of Measures | Timeframe |  | Implementati on Partner | Partner Role(s) and Resources |
|  |  |  |  |  |  | Start Date | Completion Date |  |  |
| Healthcare Access & Quality | Preventive Services for Chronic Disease Prevention and Control | 32.0 Increase the percentage of adults aged 18 years and older with hypertension who are currently taking medication to manage their high blood pressure from 77.0% to 81.7%. Ontario County Specific Objective: Increase the percentage of adults aged 18 and older with hypertension who are currently taking medication to manage their high blood pressure from 58.4% to 59.5% | Partner: UR Medicine FF Thompson Hospital Provide evidence-based education on stroke recognition and the use of emergent Emergency Medical Services (EMS) care in communities disproportionately affected by stroke hospitalizations. | Rural residents: Health care access barriers, People from racial and ethnic groups: Lower rates of hypertension treatment | Number of people reached through stroke education and trainings, Number of stroke support group sessions held, Number of stroke incidents | 1/1/2026 | 12/31/2029 | Hospital | Provide clinical educators to deliver stroke/hypertension prevention outreach in high-risk communities. Identify communities and patient groups with high rates of undiagnosed or uncontrolled hypertension. Develop and share culturally appropriate education materials. Coordinate community events and track the number of education sessions delivered. Report to Local Health Department. |
| Healthcare Access & Quality | Preventive Services for Chronic Disease Prevention and Control | 32.0 Increase the percentage of adults aged 18 years and older with hypertension who are currently taking medication to manage their high blood pressure from 77.0% to 81.7%. Ontario County Specific Objective: Increase the percentage of adults aged 18 and older with hypertension who are currently taking medication to manage their high blood pressure from 58.4% to 59.5% | Partner: UR Medicine Finger Lakes Health Geneva General Hospital Provide evidence-based stroke prevention education in communities that are disproportionately affected by a high prevalence of undiagnosed and/or uncontrolled hypertension. | Rural residents: Health care access barriers, People from racial and ethnic groups: Lower rates of hypertension treatment | Number of education/outreach events, Number of visits to online stroke education | 1/1/2026 | 12/31/2029 | Hospital | Provide clinical educators to deliver stroke/hypertension prevention outreach in high-risk communities. Identify communities and patient groups with high rates of undiagnosed or uncontrolled hypertension. Develop and share culturally appropriate education materials. Coordinate community events and track the number of education sessions delivered. Report to Ontario County Public Health Department number of events held. Report to Ontario County Public Health Department number of visits to online stroke education at flhealth.org. |
| Healthcare Access & Quality | Preventive Services for Chronic Disease Prevention and Control | 33.0 Increase the percentage of adults aged 45 to 75 years who are up to date on their colorectal cancer screening based on the most recent guidelines from 73.7% to 82.3%. Ontario County Specific Objective: Increase the percentage of adults aged 45 to 75 who are up to date on their colorectal cancer screening based on the most recent guidelines from 65.3% to 66.5% | Partner: RRH Clifton Springs Hospital and Clinic Encourage the use of client reminders by providers to increase cancer screening per Community Guide national guidelines | Rural residents: Health care access barriers | Number of practices that use client reminders | 1/1/2026 | 12/31/2029 | Hospital | Implement client reminders. Track the number of practices using reminders. Report data to Local Health Department. |

| Economic Stability | Instructions: Please review the Community Health Improvement Planning Guidance for the required elements of the Community Health Improvement Plan (CHIP) and Community Service Plan (CSP): https://www.health.ny.gov/prevention/prevention_agenda/2025-2030/docs/letter_and_guidence.pdf. Column B: Select a priority from the dropdown menu. For new priorities NOT listed in the Prevention Agenda, first identify the appropriate SDOH domain tab, then manually enter the priority name. See page 9 of the guidance for details about adding additional priorities. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Domain | Priority | Objective | Intervention | Disparities Being Addressed | Family of Measures | Timeframe |  | Implementati on Partner | Partner Role(s) and Resources |
|  |  |  |  |  |  | Start Date | Completion Date |  |  |
| Economic Stability | Poverty | 1.0 Reduce the percentage of people living in poverty from 13.6% to 12.5%. Ontario County Specific Objective: Reduce the percentage of people living in poverty from 9.2% to 9.0% | Partners: UR Medicine FF Thompson Hospital, Rochester Regional Health Clifton Springs Hospital and Clinic, UR Medicine Finger Lakes Health Geneva General Hospital Conduct regular screenings of patients for social determinants of health factors* *Justification for Modified Intervention: Food insecurity screening at hospitals relies on social work teams for follow-up and referrals. Partners in hospital settings reviewed whether social work teams had the capacity to track referrals made after a positive food insecurity screening because follow-up is a core part of the original intervention. After discussion with social workers from all three hospital systems, it was determined that referral tracking is not feasible at this time. Partners agreed to modify the approach. The revised intervention focuses on screening for food insecurity and expanding resources with plans to revisit capacity for tracking referrals later in the CHIP cycle. | People with low-income: Higher risk of food insecurity and unmet social needs | Number of screenings Performed, Positivity rates, Number of reports received by Local Health Department | 1/1/2026 | 12/31/2029 | Hospital | Maintain and expand social determinants of health screening tools in the electronic medical record workflow. Share and maintain information on local community resources. Share screening data and positivity rates with the Local Health Department. Support quality improvement efforts related to social determinants of health screening. |
| Economic Stability | Poverty | 1.0 Reduce the percentage of people living in poverty from 13.6% to 12.5%. Ontario County Specific Objective: Reduce the percentage of people living in poverty from 9.2% to 9.0% | Partner: UR Medicine FF Thompson Hospital Create healthy food pantries in hospitals to ensure food security and access to healthy food | People with low-income: Higher risk of food insecurity and unmet social needs | Number of people served by pantry | 1/1/2026 | 12/31/2029 | Hospital | Provide space and equipment within the hospital for the food pantry. Coordinate staff or volunteers to maintain the pantry. Identify patients with food insecurity through existing screening workflows. Refer patients to the pantry. Track the number of people served. Promote the pantry through hospital communications (flyers, social work teams). |

| Social & Community | Instructions: Please review the Community Health Improvement Planning Guidance for the required elements of the Community Health Improvement Plan (CHIP) and Community Service Plan (CSP): https://www.health.ny.gov/prevention/prevention_agenda/2025-2030/docs/letter_and_guidence.pdf. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Domain | Priority (select one from drop down list) | Objective (select one from drop down list) | Intervention | Disparities Being Addressed | Family of Measures | Timeframe |  | Implementation Partner (Please select one partner from the dropdown list per row) | Partner Role(s) and Resources |
|  |  |  |  |  |  | Start Date (mm/dd/y yyy) | Completion Date (mm/dd/yyyy) |  |  |
| Social & Community Context | Depression | 5.0 Decrease the percentage of adults who experience frequent mental distress from 13.4% to 12.0%. Ontario County Specific Objective: Maintain the percentage of adults who experience frequent poor mental health at 18.2% | Partner: UR Medicine FF Thompson Health Implement and promote Mental Health First Aid (MHFA) training in communities and healthcare settings. | Rural residents: Health care access barriers | Number of trainings, Number of participants | 1/1/2026 | 12/31/2029 | Hospital | Provide certified MHFA instructors. Host on-site trainings for staff and community members. Offer referral pathways for people identified through MHFA. Support data tracking and reporting for CHIP evaluation. |
| Social & Community Context | Depression | 5.0 Decrease the percentage of adults who experience frequent mental distress from 13.4% to 12.0%. Ontario County Specific Objective: Maintain the percentage of adults who experience frequent poor mental health at 18.2% | Partner: UR Medicine Finger Lakes Health Conduct standardized depression screenings during patient visits. | Rural residents: Health care access barriers | Number of screenings performed, Positivity rates | 1/1/2026 | 12/31/2029 | Hospital | Implement a screening question for depression into new electronic medical record (eRecord) to be asked at annual patient visits. Share data with the Ontario County Public Health Department. Maintain information on local community resources on flhealth.org. Report to Ontario County Public Health Department number of visits to online resources on flhealth.org. |
| Social & Community Context | Depression | 5.0 Decrease the percentage of adults who experience frequent mental distress from 13.4% to 12.0%. Ontario County Specific Objective: Maintain the percentage of adults who experience frequent poor mental health at 18.2% | Partner: RRH Clifton Springs Hospital and Clinic Track utilization data for Comprehensive Psychiatric Emergency Program | Young people: Higher rates of depression, Rural residents: Health care access barriers | Number of admissions, Number of adolescents admitted | 1/1/2026 | 12/31/2029 | Hospital | Provide Comprehensive Emergency Psychiatric Services. Support data tracking and reporting for CHIP evaluation. |