| Objective | Interventions | Family of Measures | By December 2027 | Implementation Partner | Partner Role and Partner Resources |
| --- | --- | --- | --- | --- | --- |
| 3.0 Increase consistent household food security from 71.1% to 75.9%. Seneca County Specific Objective: Maintain or increase the percentage of household food security at 77.7% | Conduct standardized screening of unmet Nutrition Security needs and provide referrals to state, local, and federal benefit programs and community-based, health-related social needs providers to address unmet needs. | Number of health practices and facilities that screen for food insecurity and facilitate referrals to supportive services Number of website visits | Screen patients at annual and new patient primary care visits for food insecurity Share data with local health department on a quarterly basis regarding number of patients screened, number of patients who worry about running out of food and patients who have run out of food | Hospital | UR Medicine Finger Lakes Health-Geneva General Hospital will: Report to Seneca County Public Health Department number of patients screened for food insecurity on a quarterly basis Report to Seneca County Public Health Department number of patients who worried about running out of food on a quarterly basis |
|  |  |  | Provide information on local resources such as WIC, SNAP, CACFP, Commodity Supplemental Food Program (CSFP) or local food pantries |  | Report to Seneca County Public Health Department number of patients who ran out of food on a quarterly basis |
|  |  |  | Share number of website visits to local resources to local public health department on a quarterly basis |  | Maintain information of local community resources such as WIC, SNAP, CACFP, Commodity Supplemental Food Program (CSFP) or local food pantries on flhealth.org |
|  |  |  |  |  | Report to Seneca County Public Health Department number of visits to food insecurity resources on flhealth.org on a quarterly basis |

Domain: Economic Stability Priority: Economic Wellbeing Focus Area: Nutrition Security

Goal: Improve consistent and equitable access to healthy, affordable, safe, and culturally appropriate foods. Disparity addressed: Socioeconomic and access barriers among rural residents

Domain: Social & Community Context

Priority: Mental Wellbeing and Substance Abuse

Focus Area: Anxiety and Stress

Goal: Increase the proportion of people living in New York who show resilience to challenges and stress.

Disparity addressed: Socioeconomic and limited access to healthcare among rural residents

| Objective | Interventions | Family of Measures | By December 2027 | Implementation Partner | Partner Role and Partner Resources |
| --- | --- | --- | --- | --- | --- |
| 5.0 Decrease the percentage of adults who experience frequent mental distress from 13.4% to 12.0%. Seneca County Speciﬁc Objective: Decrease the percentage of adults who experience frequent mental distress from 16.2% to 12.0%. | Promote and increase awareness of evidence-based mindfulness resources to reduce the negative impact of stress and trauma | Manner of outreach and data re: reach of intervention (e.g., number of outreach events, number of flyers distributed, number of website visits) | Through community partnerships, develop a list of evidence based resources addressing stress and trauma Create and maintain a directory of community resources on flhealth.org Track number of visits to resource page on website on a quarterly basis | Hospital | UR Medicine Finger Lakes Health-Geneva General Hospital will: Develop a list of evidence based community resources related to stress and trauma and post on ﬂhealth.org Share number of visits to online resources at ﬂhealth.org to Seneca County Public Health on a quarterly basis |

Domain: Healthcare Access and Quality Priority: Healthy Children

Focus Area: Preventive Services (Lead Screening)

Goal: Increase utilization of evidence-based preventive services for children.

Disparity addressed: Healthcare access barriers among rural residents, Medicaid children, Socioeconomic and Ethnicity (children in Amish and Mennonite communities)

| Objective | Interventions | Family of Measures | By December 2027 | Implementation Partner | Partner Role and Partner Resources |
| --- | --- | --- | --- | --- | --- |
| 38.0 Increase the percentage of children in a single birth cohort year tested at least twice for lead before 36 months of age from 61.0% to 70.0%. Seneca County Specific Objective: Increase the percentage of children in a single birth cohort year tested at least twice for lead before 36 months of age from 41.3% to 70.0%. | Increase the use of initial and follow-up screening protocols for high-risk children and those with elevated finger sticks, while educating parents on lead exposure prevention, following Centers for Disease Control and Prevention (CDC) recommended actions for blood lead levels, and ensuring Medicaid recipients and high-risk children are tested per federal guidelines | Increase in testing rates for both initial lead screening and follow up screening occurring within each county via New York State Immunization Information System (NYSIIS) data/LeadWeb data | Implement process to improve number of children tested two times for lead before they are 36 months of age utilizing screening protocols Educate and provide parents with resources regarding the importance of lead exposure prevention with emphasis on Medicaid children and children in the Amish and Mennonite communities Share data with local health department including age, number of children tested and number of positive results for lead at initial screening and follow up screening | Hospital | UR Medicine Finger Lakes Health-Geneva General Hospital will: Test children two times for lead before they are 36 months of age Provide parents with educational resources regarding the importance of lead exposure prevention Provide results to Seneca County Public Health Department including age, number of children tested and number of positive results for lead at initial screening and follow up screening |